## Sheet1
Sr N0. | Location | Equipment | Type | Issue | Nature | image | view image | Ref. Picture | Remarks
1 | block 1 | DBcs | Electrical | Volt meter issue in block 1 ground floor | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.00 AM.jpeg | Volt meter issue in block 1 ground floor. | Civil
2 | 1st floor power room |  | Electrical | Volt meter issue location 1st floor power room | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.00 AM (1).jpeg | Volt meter issue location 1st floor power room. | electrical
3 | block 2 |  | Electrical | Volt meter issue second floor block 2 | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.01 AM.jpeg | Volt meter issue second floor block 2 | mechanical
4 | Basement |  | Electrical | Basement dbs indication lights not working and body is rusted | Major |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.01 AM (1).jpeg | Basement dbs power lights not working | Plumbing
5 | 3rd floor power room |  | Electrical | 3rd floor power room volt meter issues Udb-2/3f 4 Pdb f2 Udb f3 Ldb 31 Same issue | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.02 AM.jpeg | 3rd floor power room volt meter issues Udb-2/3f 4 Pdb f2 Udb f3 Ldb 31 Same issue | Safety
6 | block 2 |  | Electrical | Combined picture of non functional/ voltmeter issues dbs in 3 Rd floor block 2 | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.04 AM.jpeg | Combined picture of non functional/ voltmeter issues dbs in 3 Rd floor block 2
7 |  |  | Electrical | Cable dressing issues in DBs and tags missing | Critical |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.06 AM.jpeg | Same db dressing issues
8 |  |  | Electrical | Wiring + dressing issues | Critical |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.06 AM (1).jpeg | Wiring + dressing issues.
9 | Basement |  | Electrical | Basement dbs power lights not working, it reflects no power. Functionality need to be checked | Major |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.08 AM.jpeg | Basement dbs power lights not working
10 | Power room |  | Electrical | Power room volt meter issue | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.10 AM.jpeg | Power room volt meter issue.
11 | block 1 |  | Electrical | Volt meter issue in block 1 ground floor | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.12 AM.jpeg | Volt meter issue in block 1 ground floor
12 | Block 3 floor |  | Electrical | Block 3 floor 1/ issue is volt meter | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.14 AM.jpeg | Block 3 floor 1/ issue is volt meter.
13 | block 1 |  | Electrical | Wire dressing issues block 1 3rd floor | Critical |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.15 AM.jpeg | Wire dressing issues block 1 3rd floor.
14 | block 1 |  | Electrical | Volt meter not working block 1 ground floor | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.15 AM (1).jpeg | Volt meter not working block 1 ground floor
15 | Block 1 |  | Electrical | Block 1 2nd floor , volt meter faulty | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.15 AM (2).jpeg | Block 1 2nd floor , volt meter faulty
16 | block 3 floor |  | Electrical | Volt meter + dressing issues, block 3 floor 2 | Major |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.16 AM (3).jpeg | Volt meter + dressing issues, block 3 floor 2.
17 | block 1 |  | Electrical | Volt meter issue block 1 3rd floor | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.16 AM (4).jpeg | Volt meter issue block 1 3rd floor.
18 | block 3 |  | Electrical | Volt meter block 3 , floor 2 | Minor |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.17 AM.jpeg | Volt meter block 3 , floor 2.
19 | block 1 |  | Electrical | block 1 ground floor dbs issue is 2 phase disconnected | Critical |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.17 AM (1).jpeg | Location block 1 ground floor dbs issue is 2 phase disconnected.
20 | block 1 floor |  | Electrical | Cabling issue block 1 floor 3rd | Major |  | View Image | images/WhatsApp Image 2026-09-17 at 2.47.18 AM.jpeg | Cabling issue block 1 floor 3rd
21 |  |  | Electrical | Control unit in Wapda panel in Genset 6 and 7 panel room was found non-functional | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.48 AM.jpeg | Pic 2. Pic 1 and 2 is of same LT panel wapda not working
22 |  |  | Safety | Main power supply cables were laying in unadequate way, need to be covered and protected from water/seepage | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.48 AM (2).jpeg | 1 and 2 same pic main powers line coming from cepage water
23 |  |  | Safety | Main power supply cables were laying in unadequate way, need to be covered and protected from water/seepage | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.50 AM.jpeg | Power line coming from water.
24 | Block 1 back side wall |  | Civil | Block 1 back side wall is damaged by acs outer | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.51 AM.jpeg | Block 1 back side wall is damaged by acs outer
25 |  |  | Electrical | Not proper cabling of acs wire | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.51 AM (2).jpeg | Not proper cabling of acs wire
26 | block 3 floor |  | Civil | Acs outer is damaging the wall block 3 floor | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.51 AM (3).jpeg | Acs outer is damaging the wall block 3 floor
27 | block 2 |  | Civil | Broken window 3rd floor block 2 | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.52 AM.jpeg | Broken window 3rd floor block 2
28 |  |  | Civil | Seepage damaging the wall due to AC outdoor drain water | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.52 AM (2).jpeg | Cepage damaging the wall ac water responsible
29 |  |  | Civil | Seepage issues were found in different areas of vicinity, can lead to serious damage to the structure | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.53 AM.jpeg | Cepage issues.
30 |  |  | Electrical | Improper laying of supply lines | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.53 AM (1).jpeg | Power line passing from drainage
31 |  |  | Civil | Ac damaging wall | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.53 AM (2).jpeg | Ac damaging wall
32 |  |  | Mechanical | Fan missing | Minor |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.54 AM.jpeg | Fan missing
33 | md office |  | Civil | Wall at the roof top of block 1 was found unplastered with AC piping and cables laid opening | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.54 AM (1).jpeg | Water leakage md office.
34 | block 3 |  | Electrical | Open block 3 back side dbs telephone without safety | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.55 AM.jpeg | Open block 3 back side dbs telephone without safety.
35 |  |  | Electrical | Wiring and safety issues in Dbs next to Gate No. 4 | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.55 AM (1).jpeg | Wiring and safety issues.
36 |  |  | Civil | Seepage issues in staff canteen | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.55 AM (2).jpeg | Cepage issues staff cainteen.
37 | Ground floor staff parking area |  | Civil | Ground floor staff parking area wall is broken | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.56 AM.jpeg | Ground floor staff parking area wall is broken.
38 | ground floor |  | Electrical | Parking ground floor open cable without safety | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.56 AM (2).jpeg | Parking ground floor open cable without safety.
39 |  |  | Civil | Ceiling having damages above the basement ramp block 1 | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.56 AM (3).jpeg | Cepage
40 | Ground floor |  | Electrical | Ground floor near transformers wire safety issues | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.57 AM.jpeg | Ground floor near transformers wire safety issues.
41 |  |  | Electrical | Electric wire safety issues | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.57 AM (1).jpeg | Electric wire safety issues.
42 | basement chiller room |  | Electrical | Pfi panel not working in basement chiller room block Pfi panel not working in basement chiller room block | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.57 AM (2).jpeg | Pfi panel not working in basement chiller room block Pfi panel not working in basement chiller room block
43 |  |  | Mechanical | Oil leakage and further inspection required for Genset 3 300 kva | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.58 AM.jpeg | Oil leakage and further inspection required for Genset 3 300 kva
44 |  |  | Mechanical | Genset 3 300 kva oil leakage | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.58 AM (1).jpeg | Genset 3 300 kva oil leakage
45 |  |  | Safety | Fire fighting system is off in water pump | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.59 AM.jpeg | Fire fighting system is off in water pump m
46 | Water pump room |  | Electrical | Water pump room no taging done for dbs | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.41.59 AM (1).jpeg | Water pump room no taging done for dbs.
47 |  |  | Mechanical | water leakage from valve | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.42.00 AM.jpeg | Wall leakage
48 | basement |  | Mechanical | Water leakage in water pump room basement | Critical |  | View Image | images/WhatsApp Video 2026-09-18 at 4.42.01 AM.mp4 | Wall leakage in water pump room basement.
49 |  |  | Mechanical | Pumps found non-operational, need to be checked | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.42.01 AM.jpeg | Pump not working.
50 |  |  | Mechanical | Water leakage observed in water transfer line | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.42.01 AM (1).jpeg | Leakage in wall and seals in pump
51 |  |  | Mechanical | Water leakage observed in water transfer line | Critical |  | View Image | images/WhatsApp Video 2026-09-18 at 4.42.02 AM.mp4 | Wall leakage.
52 | transformer / main meter room |  | Electrical | Proper wire arrangements missing in transformer / main meter room | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.42.02 AM.jpeg | Proper wire arrangements missing in transformer / main meter room
53 | power room |  | Electrical | PFI panel having some sections non operational, need to be investigated. | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.42.02 AM (1).jpeg | 2 power room, power factor panal not functional.
54 | power room |  | Electrical | PFI panel having some sections non operational, need to be investigated. | Critical |  | View Image | images/WhatsApp Image 2026-09-18 at 4.42.03 AM.jpeg | 2 power room, power factor panal not functional.
55 | Roof top Block 2 |  | Electrical | Roof top cabling issues | Major |  | View Image | images/WhatsApp Image 2026-09-18 at 4.42.03 AM (1).jpeg | Roof top cabling issues